## Feuille1
Planned opening		Project		Terminus		Track type	Cars [Note 2]	Length (km)	New stations	Start of construction	Status	Notes
December 2018	X	4	Phase 1	Min'an Ave.	Tangjiatuo	Heavy-rail	6As	15/06/18	9	3 December 2013	Debugging	[36]
December 2018	X	Loop	Northeastern Section (through Chongqing North Railway Station)	Chongqing Library	Haixialu	Heavy-rail	6As	30/01/18	22	28 October 2013	Debugging	[37]
2019	X	Loop	Southwestern Section (through Chongqing West Railway Station)	Chongqing Library	Haixialu	Heavy-rail	6As	20/08/18	11	28 October 2013	Under construction	[37]
	X	1	Bishan Extension	Jiandingpo	Bishan	Heavy-rail	6B	05/06/18	1	18 June 2014	Under construction	[38]
	X	5	Phase 1 - Southern Section	Xietaizi	Tiaodeng	Heavy-rail	6As	15/08/18	13	3 December 2013	Under construction	[36]
2020	X	5	Phase 1 - Central Section	Dashiba	Xietaizi	Heavy-rail	6As	04/07/18	2	3 December 2013	Under construction	[36]
	?	S5	Jiangjin line - Phase 1	Tiaodeng	Shengquansi	Heavy-rail	6As	26/07/18	6	10 June 2015	Under construction	[39]
	X	6I	International Expo branch - Phase 2	Yuelai	Shaheba	Heavy-rail	6B	13.71	7	28 October 2016	Under construction	[40]
	X	9	Phase 1	Xinqiao	Xingke Ave.	Heavy-rail	6As	32.3	25	28 September 2016	Under construction	[41]
2021	X	10	Phase 2	Lanhua Rd.	Liyuchi	Heavy-rail	6As	11/03/18	8	28 October 2016	Under construction	[40]
	X	9	Phase 2	Xingke Ave.	Huashigou	Heavy-rail	6As	01/10/77	5	Late 2017	Under construction	[41]
2022	2025	4	Phase 2	Tangjiatuo	Shichuan	Heavy-rail	6As	32.46	12	2018	Planned	[42]
	2025	5	Phase 2	The Garden EXPO Center	Yuegangbeilu.	Heavy-rail	6As	08/05/18	7	2018	Planned	[42]
	?		branch	Fuhua Rd.	Tiaodeng S.	Heavy-rail	6As	29.45	19	2019	Planned	[42]
	?	S5	Jiangjin line - Phase 2	Shengquansi	Dingshan	Heavy-rail	6As	01/04/61	2	2018	Planned	[43]

Planned → ?